## RFC Action Tracker
Roads, Footpaths and Commons Action Tracker as of 26/01/2023
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
ITEM | DATE of Meeting | SUBJECT | ACTION | BY WHOM | PROGRESS | DEADLINE | RAG*
22-016 | 2022-10-20 | Management of commons | To look at using volunteers to assits with the management of the commons. | AM |  | 2022-12-31 | G
22-018 1 | 2022-10-20 | Swallowfield Community SpeedWatch | Liaise with Swallowfield's Transport Lead and SpeedWatch Co-ordinator | AM |  | 2022-11-30 | G
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair mortar with lime mortar | Clerk/Custodian | Waiting for warmer weather | 2022-11-30 | G
|  |  | Apply wac coating to brass surfaces | Clerk/Custodian | Completed | 2022-11-30 | G
22-018 3 | 2022-10-20 | West End Road Car Park | Establish management of border | Clerk/AM/SH | Ongoing | 2023-01-01 | G
22-018 4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath | Arrange to meet with a WBC officer to review the issues | Clerk/AM | Completed - WBC & contractor will review the footpath. | 2022-12-31 | G
22-018 5 | 2022-10-20 | Windmill Common Tree Survey | To obtain quotes and place an order up to the value of agreed budget of £1,500 | Clerk/AM | Completed | 2022-12-31 | G
22-018 6 | 2022-10-20 | Brewery Common and Summerlug | Meet with WBC Tree officer to review ongoing management | Clerk/AM/DM/CL | Completed | 2023-01-31 | G
22-019 | 2022-10-20 | West End Road Car Park Brambles | Custodian to remove the brambles | Clerk/Custodian | Completed | 2022-11-30 | G
21-027 3 | 2022-01-25 | War Memorial budget £250 | To seek advice as to how the War Memorial should be cleaned | Clerk/CL | Completed | Ongoing | G
22/007 1a | 2022-06-30 | TME Licence | Submit signed Licence to WBC | Clerk | Completed | 2022-07-14 | G
22/007 1b | 2022-06-30 | CSW signs budget £1,500 | Establish location/ number of signs required | Clerk | Completed | 2022-07-07 | G
|  |  | Seek permission from and liaise with WBC re installation | Clerk | Completed | 2022-07-21 | G
|  |  | Purchase signs | Clerk | Completed | 2022-07-28 | G
|  |  | Install signs | Clerk | Completed | 2022-08-28 | G
22/007 1c | 2022-06-30 | Deployment of ASWC/SID | Test ASWC to ensure it is working | MD/JW | Completed | 2022-07-07 | G
|  |  | Obtain site approval for SID locations | Clerk | 2 Risk Assessments outstanding | 2022-07-21 | A
|  |  | Seek volunteers for TME | AM/Clerk | Outstanding | 2022-07-14 | A
|  |  | Review of Progress made | Sub-Group | Completed | 2022-07-28 | G
22-007 3a | 2022-06-30 | Commons | Explore what management options are available | AM |  | 2022-08-28 | G
22-007 3b | 2022-06-30 | Windmill Common vegetaion | Cut back vegetation alongside Longmoor Lane | Clerk/Custodian | Completed | 2022-07-28 | G
22-008 | 2022-06-30 | Victoria Road tree works | Write to WBC for a response to the complaint received | Clerk/AM | Completed | 2022-07-07 | G