## RFC Action Tracker
Roads, Footpaths and Commons Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
ITEM | DATE of Meeting | SUBJECT | ACTION | BY WHOM | PROGRESS | DEADLINE | RAG*
22-029 4 | 2022-02-02 | Windmill Common Tree Survey | PO to be issued to Sapling Arboriculture | Clerk | Completed | 2023-02-28 | G
22-029 3 | 2022-02-02 | West End Road Car Park - neighbour painting of fence | Agreed budget of £100 as a contribution towards the cost. | Clerk | Neighbour is oragnising the painting | Dependent on neighbour | G
22-029 2 | 2022-02-02 | Management of commons | Review of current status of commons as a basis of framework for planning future action. | MS |  | 2023-06-29 | G
22-029 1 | 2022-02-02 | SID and ASWC | Seek approval for 3 additional TME sites for the SID | Clerk | In progress | 2023-06-29 | R
|  |  | Confirm if WBC approval is needed for deploying the ASWC at identified sites. | Clerk | Cheryl Evans confirmed it is not required. | 2023-06-29 | G
|  |  | AM to write text for social media seeking volunteers | AM/Clerk | Ongoing | 2023-06-29 | A
22-018 1 | 2022-10-20 | Swallowfield Community SpeedWatch | Liaise with Swallowfield's Transport Lead and SpeedWatch Co-ordinator | AM |  | 2022-11-30 | R
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair mortar with lime mortar | Clerk/Custodian | SH is working with custodian. | 2022-11-30 | R
22-018 3 | 2022-10-20 | West End Road Car Park | Establish management of border | Clerk/AM/SH | Not yet done | 2023-01-01 | R
22-018 4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath | Arrange to meet with a WBC officer to review the issues | Clerk/AM | Contact has been made with WBC officer but awaiting feedback | 2022-12-31 | R