## Sheet1
Fairground and Cemetery Budget Tracker 2023/24 - Cost Centre 301 as at 30/06/2023
All figures are ex- VAT
Nominal Code | Project | Current Budget Detail | Current Budget Agreed | Amount Spent to Date | Notes re Amounts Spent to Date | Balance | Subsequent POs Raised/Invoices Received | Notes re Subsequent POs Raised/Invoices Received | Amount(s) Committed | Balance
4200 | Cemetery Grass Cutting | Current contract started in January 2022 and includes 16 x grass cuts, 3 x weed applications & 2 x heddge trims. The additional budget for 23/24 allows for an increase in revenue costs for the cemetery extension grounds maintenance. | 2640 | 65.65 | 1 x cut | 2574.35 | June payment | Cut & spray | 95.95 | 2478.4
4201 | Cemetery General Maintenance |  | 1000 | 0 |  | 1000 |  |  | 0 | 1000
4202 | Cemetery Lease Rental |  | 250 | 0 |  | 250 | June payment |  | 62.5 | 187.5
4300 | Fairground Grass Cutting | Current contract started in January 2022 SCS and includes 12 x monthly fees based on 19 "fortnightly visits". One off costs for grazing area cuts are charged for sperately. | 4400 | 0 |  | 4400 | June payment | For April and May | 640.24 | 3759.76
4301 | Fairground Maintenace/Expense | Includes equipment manitenace; annual tennis court clean; electricity; waste collection, remedial works, Christmas tree; water charge; and sundries (i.e. refuse sacks, tools, seed, weedkiller, locks). | 12730 | 198 | Electricity, refuse sacks, petrol & waste collection | 12532 |  |  |  | 12314.3
[7 empty] | June payment | Tools, paint, seeds. Soil, lock, waste collection | 217.7
4302 | Dog Bin Waste Disposal |  | 2548 | 196 | April charge | 2352 |  |  | 0 | 2352
4303 | Play Area Maintenance | The 2023/24 budget was for an estimate of 'normal' level of preventive and reactive maintenance. It was increased to allow for the upkeep of the fitness equipment. | 7700 | 342.5 | 1 x RoSPA and 1 x quarterly maintenance inspection | 7357.5 | 2312/2314 | Play area remedial works | 1140 | 6217.5
4309 | Pillbox Maintenance | New contract started in January 2022 & placed with Tactical Facilities at a total cost of £120.00 for 4 maintenance cuts. Budget figure allows for 1 x tidy-up cut at the end of winter/beginning of spring, 4 scheduled maintenance cuts and other on demand cuts as requested | 210 | 34.34 | 1 x cut. | 175.66 |  |  | 0 | 175.66
4320 | Fairground Lease Rental | Rent review took place in September 2020 and new rate is £2701. This will next be reviewed when the current lease expires in 2027 | 2701 | 0 |  | 2701 |  |  | 0 | 2701
|  |  | 34179 | 836.49 |  | 33342.51 |  |  | 2156.39 | 31186.12
`
Fairground and Cemetery EMRs
|  | EMR Detail | Opening Balance 01/04/2023 | Amount Spent to Date | Notes re Amounts Spent to Date | Balance | Other POs Raised | Notes re Other Pos Raised | Amount(s) Committed | Balance
4210/ EMR 320 | Cemetery Extension | Reserve held for footpath works , design and landscaping. | 40555 | 0 |  | 40555 | 2306 | TGMS for design & assistance with the tendering process and monitoring of construction. | 6770 | 33785
4306/ EMR 326 | Tennis Courts | This EMR is being built up achieve £50k by March 2029. | 46666 | 0 |  | 46666 |  |  |  | 46666
EMR | Carried over from 2021/22 | £1,000 is required for the conservation boards. | 1000 | 0 |  | 1000 |  |  |  | 1000
| Totals |  | 88221 | 0 |  | 88221 |  |  | 6770 | 81451
Fairground and Cemetery Agreed CIL Spend
|  | EMR Detail | Amount Agreed | Amount Spent to Date | Notes re Amounts Spent to Date | Balance | Other POs Raised | Notes re Other Pos Raised | Amount(s) Committed | Balance
CIL EMRs | Full Council 13/10/22 | Fairground Utility Square | 20000 | 0 |  | 20000 |  |  |  | 20000
CIL EMRs | Full Council 13/10/22 | Fairground Utility Square | 20000 | 0 |  | 20000 |  |  |  | 20000
| Totals |  | 40000 | 0 |  | 40000 |  |  | 0 | 40000