## RFC Action Tracker
Roads, Footpaths and Commons Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
ITEM | DATE of Meeting | SUBJECT | ACTION | BY WHOM | PROGRESS | DEADLINE | RAG*
23/008 | 2023-06-29 | Skunk cabbage | Establishment the management of thIs invasive plant. | MS |  | ?
23/008 | 2023-06-29 | Gigaclear work | Take photos and write to Gigaclear regarding the poor state of the repair of the footways and road following the recent works | SH/Clerk |  | 2023-07-17
23/007 5 | 2023-06-29 | SID & ASWC | To run a speed watch campaign | Trained councillors |  | ?
|  |  | To co-ordinate the management and deployment of the SID and ASWC | MD |  | Ongoing
|  |  | Subgroup to meet and consider publicity and recruitment drive for volunteers | Subgroup |  | ?
|  |  | Approach walking group re vounteering for SID/ASWC deployment | GB | MD has been in touch with 2 wlaking group volunteers. | Completed
23/007 2 | 2023-06-29 | Tree Survey | Obtain quotes for the tree work | Clerk |  | 2023-08-31
23/007 1 | 2023-06-29 | Management of commons and land | Continue with the review of commons and other land and to undertake a survey with other third parties. | MS/other local third parties |  | ?
|  |  | Meet with Englefield to review the management of Windmill Common | SH |  | 2023-08-16
|  |  | Undertake a review of the Commitees TofR | Clerk/Council |  | 2023-09-30
22-029 3 | 2022-02-02 | West End Road Car Park - neighbour painting of fence | Agreed budget of £100 as a contribution towards the cost. | Clerk | Neighbour is oragnising the painting | Dependent on neighbour | G
22-029 1 | 2022-02-02 | SID and ASWC | Seek approval for 3 additional TME sites for the SID | Clerk | In progress | 2023-06-29 | R
|  |  | AM to write text for social media seeking volunteers | AM/Clerk | Ongoing | 2023-06-29 | A
22-018 1 | 2022-10-20 | Swallowfield Community SpeedWatch | Liaise with Swallowfield's Transport Lead and SpeedWatch Co-ordinator | AM |  | 2023-09-30 | G
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair mortar with lime mortar Complete Risk Assessment Borrow elevated works platform | Clerk/SH/Custodian |  | 2023-09-30 | G
22-018 3 | 2022-10-20 | West End Road Car Park | Establish management of border | Clerk/AM/SH | Not yet done | 2023-01-01 | R
22-018 4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath - WBC is arranging for the footpath to be fresurcaed with Flexipave but, due to current commitments, not within the next year. | Clerk to check back with AC in March 2024 | Clerk |  | 2024-03-31 | G