## RFC Action Tracker
Roads, Footpaths and Commons Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
ITEM | DATE of Meeting | SUBJECT | ACTION | BY WHOM | PROGRESS | DEADLINE | RAG*
23/018 | 2023-10-19 | Overgrown hedges | Finalise text for cards advising residents to cut back their hedge | AM | Complete | 2023-10-31 | G
|  | Overgrown hedges | Report overgrown hedges via Whatsapp Group. Add to tracker, deliver card and leaflet, update tracker | ALL |  | None | G
23/018 | 2023-10-19 | Rights of Way Improvement Plan | Review draft ROWIP and formulate response | GB, DM, AM, MS |  | 2023-11-30 | A
23/019 | 2023-10-19 | Potholes | Advise locations of potholes reported | DK |  | 2023-10-31 | R
23/019 | 2023-10-19 | New Guidance on Biodiversity | Review | AM, MS |  | 2023-11-30 | A
23/023 | 2023-10-19 | School Parent Parking on The Street | Inform residents of SMPC role Request onsite meeting with WBC | Clerk Clerk | Complete - meeting arranged for the 18th of Jan
|  |  | MS to confirm exact location of skunk cabbage. | MS
23/008 | 2023-06-29 | Skunk cabbage | Clerk will inform West Berkshire Council (WBC) of the location of skunk cabbage that has been spotted in the parish | MS/C | Complete - WBC confirmed they would look into it but no further update | 2023-10-31
23/008 | 2023-06-29 | Gigaclear work | WBC officers and Dist. Cllr Poole are following up on the reinstatement works on Highways land. A letter will be sent to Gigaclear, copied to WBC, regarding the reinstatement works on unadopted roads. |  | An email was sent and Gigaclear have responded asking for more information which has been supplied. Now waiting for a further response.
23/007 5 | 2023-06-29 | SID & ASWC/ Speedwatch | Produce text to recruit further volunteers for SID & ASWC | AM | In progress | 2023-10-31 | G
|  |  | Attend WBC CSW Seminar | AM, GB | Complete |  | G
|  |  | Request copy of the letter sent to reported offending vehicle owners, and number of letters and type sent out | Clerk | Complete | 2023-10-31 | G
|  |  | Application placed for 4 additional ASWC locations | MD | In progress |  | G
23/007 2 | 2023-06-29 | Tree Survey | Obtain quotes for the tree work Advise on suitable replacement trees | Clerk MS | Complete - on agenda | 31/10/2023 31/10/2023 | G
23/007 1 | 2023-06-29 | Management of commons and land | Distribute review report on Management of Commons to all RF&C Committee members for discussion at next meeting | MS |  | 2023-10-31 | G
|  |  | Meet with Englefield to review the management of Windmill Common | SH | Update requested 07/11/2023 | 2023-08-16 | R
|  |  | Undertake a review of the Commitees TofR | Clerk/AM |  | 2023-09-30 | R
22-029 3 | 2022-02-02 | West End Road Car Park - neighbour painting of fence | Agreed budget of £100 as a contribution towards the cost. | Clerk | Neighbour is oragnising the painting | Neighbour has decided not to proceed. | R
22-029 1 | 2022-02-02 | SID and ASWC | Seek approval for 3 additional TME sites for the SID - application in progress | MD | In progress | 2023-06-29 | G
22-018 1 | 2022-10-20 | Swallowfield Community SpeedWatch | Liaise with Swallowfield's Transport Lead and SpeedWatch Co-ordinator | AM | Complete Swallowfield have suspended ASWC activity | 2023-09-30 | G
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair mortar with lime mortar Complete Risk Assessment Borrow elevated works platform | Clerk/SH/ Custodian | Lime works being undertaken in May | 2023-09-30 | G
22-018 3 | 2022-10-20 | West End Road Car Park | Establish management of border | Clerk/AM/SH | Not yet done | 2023-01-01 | R
22-018 4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath - WBC is arranging for the footpath to be fresurcaed with Flexipave but, due to current commitments, not within the next year. | Clerk to check back with AC in March 2024 | Clerk |  | 2024-03-31 | G