## RFC Action Tracker
Roads, Footpaths and Commons Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2025-02-06
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
22-029 3 | 2022-02-02 | West End Road Car Park management of border | Plant the border with suitable plants and use bark as a weed suppressant. | Clerk/MS/Custodian | To be done |  | MS has suggested to purchase drought resistant plants from any nursery or online. Deadline was extended beyond Feb. | 2025-03-01 | G
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair the mortar with lime mortar | Clerk/SH/ Custodian | Works were to be undertaken in May but not done |  | The War Memorial was cleaned in October 2023. Confirmed with SH that from May 2025 - the mortar works need undertaking and brass needs cleaning. Deadline extended. | 2025-05-01 | A
22-018 4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath - WBC is arranging for the footpath to be resurfaced with Flexipave but, due to current commitments, not within the next year. | Check if and when the resurfacing works are being undertaken. | Clerk | Not yet done |  | Emails sent to WBC (A Coxon) on the 10/10, 05/12 and 17/12, 9/01. Deadline extended. | 2025-03-03 | A
23/007 1 | 2023-06-29 | Management of commons and PC owned land | To review Brewery Common report and establish further actons needed. | MS | Brewery Common 50% complete and reported |  | MS has completed and given advise on haycuts- to share at Feb meeting and agree actions. | 2025-02-06 | G
|  |  | To review the outcome of the meeting that took place with Richard Edwards re Windmill Common on the 27/06/24 and establish further actions needed | MS | Meeting took place |  | MS has completed - to share at Feb meeting and agree actions. | 2025-02-06 | G
23/029 | 2024-02-01 | Management of commons and PC owned land | Approach Greening Mortimer regarding work on commons/land improvement |  | Greening Mortimer are aligned. 4 volunteers secured at GM relaunch. Waiting for projects to be defined |  | Action plan received | Ongoing | G
24/008 | 2024-06-20 | ASWC Software Update | Purchase & install | MD/Clerk | Will be undertaken when the camera is not in use |  | Completed- just waiting to pay in Feb then can be closed | 2025-01-31 | G
24/008 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | Clerk |  |  | No response found so email sent to WBC PROW asking for an update on footpath issues in the parish, chased email 16/01 | 2024-12-01 | G
24 | N/A | Hedges | Establish with the APM trustees if the hedge has been cut as per the request of 17/07 APM | Clerk |  |  | Email sent to member of Trust JH on 16/01 | 2024-11-15 | A
24/021 3 | 2024-10-17 | Brewery Common Tree Survey | Establish the responsibilities of WBC for managing Brewery Common under the "Scheme" | Clerk |  |  | Email response from Paul Hendry received- to be discussed at meeting of 06/02 | 2024-12-01
24/012 4 | 2024-10-17 | SID & ASWC | Add sites: St Johns triangle and Methodist Church | MD/Clerk |  | New | MD has applied for additional sites | 2025-02-06
|  |  | Review other potential sites and look to add | MD |  | New |  | 2024-11-30
|  |  | Look at alternative ASWC systems | DK |  | New | chased DK 20/01 | 2024-11-30
|  |  | Establish deployment rules for SID and Sentinels | GB/Clerk |  | New | Clerk has sent deployment Rules onto chair of committee. ? can be removed from tracker. | 2024-11-15
|  |  | Advertise for additional volunteers | DM/Clerk | Ongoing | Follow up |  | Ongoing
|  |  | Add to full Council agenda re councillors as volunteers | Clerk |  | New | Discussed at meeting on 14/11/24 - no additional councillor volunteers identified | Ongoing
|  |  | Speeding summary for communicating | MD |  | New | Asked MD for summary | 2024-11-15
24/012 5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist | DM/Clerk |  | Write to WBC | Follow up email sent to WBC HTAdmin on 17/12 and 16/01 asking for further information regarding managing vegetation under devolved powers. A member of the team is looking into this. | 2024-11-15
24/021 6 | 2024-10-17 | Stra FP42/43 Footpath leading from West End Road near the APMF to Drury Lane | Seek to connect footpaths as one PROW | GB/Clerk | Formally write to Englefield Estate as landowners, referring them to previous correspondence with the farmer and asking them to agree to join the paths together as one contiguous footpath. | Write to Englefield Estate | Email sent to Englefield on 19/11/2024 E Crookes confirmed they would explore this before coming back to us. chased response 16/01, E Crooks responded- has visited site and will get back to council. | 2024-11-15
24/021 7 | 2024-10-17 | St Marys School and The Steet Parking - liaise with WBC re….. | Repainting of the yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways | Two positive responses. Leave decision until response re yellow lines from WBC |  | 2024-11-15
[5 empty] | Awaiting response from WBC re refurbishing existing yellow lines |  | GB has sent photos to Gareth Dowding on 15/01, he has replied and said would pass to refresh tem to instruct them to complete. | 2024-11-15
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns and Pitfileld Lane up The Street |  | 18 month wait to assess yellow lines request. |  | Gareth Dowding confirmed that still 18 month waitlist on this | 2024-11-15
|  |  | Road sign showing T junction at Mortimer Lane/The Street should show staggered crossroads? |  | New at meeting - raised by member of public living in Church Farm Barns | Refer to WBC | Not yet done, will be discussed at meeting | 2025-02-06
24 | 2024-10-17 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield’s land and connecting to Drury Lane. | Clerk |  | Awaiting establishment of public open space and paths around SUDS ponds |  | Ongoing