## RFC Action Tracker
Estate Management Committee Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2025-05-22
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair the mortar with lime mortar | Clerk/SH/ Custodian | Works were to be undertaken in May but not done | Leave deadline as 01/05/2025 | The War Memorial was cleaned in October 2023. Confirmed with SH that from May 2025 - the mortar works need undertaking and brass needs cleaning. Deadline extended. | 2025-05-01 | A
23/029 | 2024-02-01 | Management of commons and PC owned land | Approach Greening Mortimer regarding work on commons/land improvement |  | Greening Mortimer are aligned. 4 volunteers secured at GM relaunch. Waiting for projects to be defined | MS to find out who the volunteers are | Action plan received | Ongoing | G
24/021 3 | 2024-10-17 | Brewery Common Tree Survey | Establish the responsibilities of WBC for managing Brewery Common under the "Scheme" | Clerk |  | GB will put Will Strang in Touch with MS | Email response from Paul Hendry received- to be discussed at meeting of 06/02 | 2024-12-01 | A
24/012 5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist | DM/Clerk | The Clerk to chase again mid feb | Write to WBC | Email received on 04/02/25 asking if parish would be interested in devolved powers, responded positively and asked for next potential steps. Chased 30/06/25 | 2025-06-26
25/006 | 2025-05-22 | Cemetery regulations breach letter | The Clerk was to prepare a draft template letter to send to users who breach the cemetery regulations | Clerk |  |  | The clerk has drafter the letter and sent to the Chairman who has suggested an edit, the clerk has compelted the edited document and it will be sent to users when needed. 03/06 | 2025-07-24 | G
25/009-4.a | 2025-05-22 | Cemetery extension ongoing maintenance | The Clerk to contact current maintenanc eprovider (Tactical) to get a spec and a quote for ongoing mainteneance contract. | Clerk |  |  | Meeting with tactical booked 12/6/2025, awaiting quote | 2025-07-24 | G
25/009-4.b | 2025-05-22 | Cemetery extension gap in hedge | The Clerk to contact the current contractors (White Horse) about filling the gap in the boundry hedge at the site following completion. | Clerk |  |  | Emailed white horse 03/06/225, chased 10/06/2025, White horse confirmed they will be completing this FOC. | 2025-07-24 | G
25/012 | 2025-05-22 | Electricity cabinets remedial work | Following a request to alter quotes in February 2025 Stanley Electrical services still need to alter remedial works quotes | Clerk |  |  | After chasing Stuart came back on 10/06/25 saying he will reconfirm costs wih suppliers and get back to us | 2025-07-10 | G
25/015 3 | 2025-05-22 | Fairground Fence | R Saunders and S Hill to create a spec for the replacement of the Fairground Fence running along The Street. | RS/SH |  |  |  | 2025-07-24 | G
25/015 4 | 2025-05-22 | Playground Equipment Resurfacing | A spec for the resurfacing of some of the playground equipment surface is needed followed by obtaining quotes. | SH/Clerk |  |  | S Hill advised to look through the recent ROSPA and obtain quotes with lined items for the High and Medium risk pieces of equipment. Invitations to 3 contractors for quotations sent. | 2025-07-24 | G
25/009 5 | 2025-05-22 | Fairground information boards | R Saunders to develop draft designs and explore potential suppliers | RS |  |  |  | 2025-07-24 | G