## RFC Action Tracker
Community Committee Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-04-23
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | DEADLINE | RAG*
| 2025-07-31 | Community outreach, Tennis/Cricket/ SPMF/MVP | DM- MVP AR- Tennis/Cricket JH- APMF | AR/JH/DM | Cllr Williams will engage with the Mortimer Football Club |  |  | 2025-09-30 | G
25/060.4 | 2026-01-29 | Arts Festival | JH to investigate options for arts festival | JH |  |  |  | 2026-04-23
25/060.4 | 2026-01-29 | Village Market | Investigate options for Village market | DK |  |  |  | 2026-04-23
25/060.4 | 2026-01-29 | Utility square usage | KS to look into flagpole | KS |  |  |  | 2026-04-23
26/060 5 | 2026-01-29 | Investigate Youth Council | DM to create a paper for next meeting | DM |  |  | DM has investigated and will present to Committeee on 23/04 | 2026-04-23
25/060 5 | 2026-01-29 | Ice skating rink | Clerk to investigate who Burgfield Parish Council use for their Ice skating rink | Clerk |  |  | The Office has sent the research through to the Chairman the cost is expensive, The Office will speak to BPC to see if a Councillor will speak to DM. | 2026-04-23

## Previous
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | DEADLINE | RAG*
25/008-1 | 2025-05-29 | Communicating information from Thames Water to the public following the site visit | To establish what information needs sharing and to then share that information. | The Clerk | Paul Hampton emailed on 3/6/25 requesting information to be shared |  | Completed | 2025-07-01 | G
25/010 ii | 2025-05-29 | Re-Evaluation of the Communications Policy | Following the committee meeting Cllr Bridgman was to re-organise the policy to extract items to be used in the code of conduct, the committee will then re-evaluate the policy | GB/Committee | GB has re-organised the policy, code of conduct to go to Full council on 12 June, the committee to reorganise- completed |  | Completed | 2025-07-31 | G
25/010 iii | 2025-05-29 | Community Grant Policy and application form | To reword the community grant policy for full council To reword the application form. To advertise the community grant time frame | GB/Clerk | GB has reqorded the community grant policy, The Clerk has reworded the application form. Once Full council approves these on 12 June, the clerk will go back to the current applicants and publicise the new time frame. - completed |  | Completed | 2025-07-24 | G
25/011 | 2025-05-29 | MVP | To organise a stall for Funday and to affiliate with MVP | Clerk | Stall organised, the Clerk to confirm with the council whether a table/chair will be needed, what game will be run. Affilation forms received and to be completed 09/06/2025- completed |  | Completed | 2025-07-05 | G
25/011 4 | 2025-05-29 | Whatsapp | To organise a community committee whatsapp group to share new ideas | Clerk | completed |  | Completed | 2025-07-31 | G
25/011 5 | 2025-05-29 | Defibrillators | To respond to the AED charity regarding what they can do for us | Clerk | Charity was responded to but no further information that was relevent was given, the Clerk has responeded further and is awaiting a response 09/06/25 |  | Completed | 2025-07-01 | G
25/011 3 | 2025-05-29 | T shirts | K Strong and R Saunders to organise SMPC T shirts for Funday | KS/RS | DD chased RS/K strong re T shirts- completed |  | Completed | 2025-07-05 | G
25/009 | 2025-05-29 | Arrange face to face meeting with WBC re cycleway regarding what WBC will cover for the highways portion of cycleway | D Kilshaw to arrange meeting | DK | Clerk has sent request to Jon Winstanley who has passed this onto D Wildish, a meeting is being arranged for 13 August between 1-3pm. |  |  | 2025-07-01 | A
25/011 1 | 2025-05-29 | New Newsletter format options | N Carter to inquire with Burghfield PC regarding email districbution lists. | NC |  | The Clerk will contact BPC |  | 2025-07-31 | A
25/011 5 | 2025-05-29 | Defibrillators | To organise training for chosen defibrilator checkers | Clerk/Assistant Clerk | Sallyann will organise training during the quieter months of summer. |  |  | 2025-08-31 | G
25/014 | 2025-05-29 | Bus Shelters | To follow up on WBC potential to fund bus shelters to the parish | Clerk | The clerk reported this to FC on 12/6/2025, The Clerk is arranging a meeting with HG/WBC on site. |  |  | 31/06/2025 | A
| 2025-07-31 | Questionnaire | HG to produce questionnaire for approval of the committee | HG/DD/JH |  | As per Action |  | 2025-08-08 | G
| 2025-07-31 | Questionnaire | everyone to contribute to questionnaire and circulate to Committee | all |  | As per Action |  | 2025-08-15 | G
| 2025-07-31 | Electronic news bulletin | Electronic bulletin board, first draft- no content just layout. | DD/HG/JH/DM |  | As per Action |  | 2025-08-31 | G
| 2025-07-31 | Electronic news bulletin | Final Electronic newsletter to go out. | DD/HG/JH/DM |  | As per Action |  | 2025-09-30 | G
| 2025-07-31 | Electronic Notice board | AR and the Clerk to contact a Parish who currently use the Electronic Noticeboards and discuss potential locations with existing businesses. | AR/ |  | As per Action |  | 2025-08-31 | G
| 2025-07-31 | Council surgeries- add another round | The assistant Clerk to create a new poster with further dates |  |  | As per Action |  | 2025-08-08 | G
| 2025-07-31 | Scarecrow trail WP | To develop a scarecrow for the scarecrow trail- Entry deadline Monday 22 September 2025 | HG, DK, KS, DD |  | As per Action |  | 2025-09-22 | G
| 2025-07-31 | Long term app/ Social media | Working Party to produce a proposal. | RS/JH/DD |  |  | Meeting not arranged | interim update- 30/09/25 | G
25/014 | 2025-05-29 | New Logo Design | KS to investigate designing a new Logo based on Mortimer Family Heraldry. | KS | KS has sent a report for presentation at the meeting of the Community Committee 29 January 2026 | KS to proceed with final draft and vectoring of the logo as discussed in the meeting. |  | Circulate by Email 01/04/2026 | G
25/060.1 | 2026-01-29 | Community Award | Develop and add the Community Award nomination form to the website (urgent) | DD/RS |  |  |  | 2026-02-04
25/060 2 | 2026-01-29 | Photography competition | Write up the specifications for the photography competition, advertise it, establish ways to enter |  |  |  |  | 2026-02-16
25/060.2 | 2026-01-29 | Community Competition | Research and implement arrangements for community voting for the photography competition | DD/JH |  |  |  | 2026-02-09
Note on G21: Danusia: I don't think Kevin can do the vectoring - Ryan said he could do this I think