## Highways
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2025-12-11
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Email exchange on 7 July and WBC said they would re-inspect and decide next steps. Chased 22 Aug 2025. A Coxon inspected the route on 11 September 2025. He noted the following: There are a couple of locations where some minor repairs would be useful where surface defects are appearing. Whilst currently it is within the guidelines, there is no doubt the condition will not improve, and maintenance sooner rater than later will be preventative. At this time the whole route is in reasonable condition, however, it will benefit from some improvement in the future. This may be in the form of repairs and surface treatment. If there is any further or new deterioration, especially trip hazards, please log the issue and we will inspect and repair | Review in 9 months time |  | 2026-06-30 | G
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | Awaiting establishment of public open space and paths around SUDS ponds. | Write to Edward Crooks at Engelfield and TA Fisher where they are with the planning of the footpath. | Update from Edward Crooks on 21 November 2025: 1. My colleague Harriet met with James Strang, the tenant of the field between MOR006 and Dury Lane to discuss the practicalities and what the Estate will do in terms of signage, fencing, gates and the Drury Lane access point. We’re in the process of working up a plan/specification to execute that, getting quotes from contractors etc. 2. I’ve liaised with Steve Davies at T A Fisher over timing from their viewpoint, including the progress of the development, health & safety, Heras fencing etc. I understand that the development is not fully complete yet but they envisage partial opening up of the open space and we’ll keep in touch with them over the timing of the permitted path opening. In summary, it’s moving forward and just a case of finalising what works are required, then agreeing the detail and timing with James and TAF | Ongoing | G
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | Clerk | chased Kofi Adu-Gyami on 22/08/2025. Response received 25/8/25. Kofi has chased with relevant team and they should be contacting interested parishes soon. | Chase Kofi Adu-Gyami | Andrew Reynolds from WBC responded on 9 October with new process. It was discussed at the Planning meeting on 30 October and Danusia agreed to come up with a response. A response was sent by the office on 4 November as it was agreed that the new process will unlikely improve the current situation. | Ongoing | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | Clerk | chased 22/08/2025. Edward Crookes responded 26/8 and said he had visited the path about 10 days ago and has contacted Stuart Higgins the Definitive Map officer at WBC and is waiting to hear back to put the necessary conditions in hand. | Contact Edward Crooks and Stuart Higgins | Edward Crooks sent update on 21 November 2025. West Berkshire had suggested contacting Hampshire to correct an unrecorded section (B–C) of a path caused by errors during the 1991 boundary changes. Hampshire has responded helpfully and outlined two possible options, though one would require a formal delegation of functions between the authorities and would likely be slow and inefficient. Hampshire’s preferred, simpler option is for West Berkshire to record the missing link themselves, either via a Definitive Map Modification Order (to correct an error) or through a Highways Act 1980 creation agreement with the landowner. The next step is to discuss these options with West Berkshire—ideally in person. Meanwhile, the Estate agrees to allow public use of the route marked with purple crosses as a permitted footpath until further notice. | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways. Two positive responses - decision left until yellow lines repainted. | On hold. |  | Ongoing | G
[5 empty] | chased 22/08/2025. Garteh Dowding responded 22/08/25 - The current programme is fully committed for this financial year. However, The Street Mortimer from Strawberryfields to junction with Bloomfield Hatch Lane has been identified for next years programme along with other sites in the District. | Review in 9 months time |  | 2025-06-30 | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | chased 22/08/2025. Alex Drysdale responded 27/08/25 and said current position is that the request will remain on file and not be included in any immediate parking scheme | GB/AR and ST to write back and agree the text | Alex Dryscale from WBC responded 20/11/25. There is no further update on SMPC’s parking requests. Current priorities are three parking scheme consultations (Amendments 35, 36, and the upcoming Amendment 37), so SMPC’s requests are on file for possible inclusion in future schemes. However, more evidence of regular traffic disruption is needed to justify restrictions on the road west of Pitfield Road, as four site visits during school pick-up times showed no routine dangerous or obstructive parking—only occasional issues during special school events. When the area is eventually reviewed, the council will need to work closely with the school to understand their concerns and secure their support, as this helps reduce objections during consultation. Previous proposals have faced significant objections from parents, and despite expectations that children walk to school, many do not, which affects community response to restrictions | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | chased 22/08/2025. Responded 27/8/25 - With the reported issue on The Street upwards of Pitfield Lane in particular we would need to investigate whether there is a reasonable and realistic solution to the school parking, as we’re not entirely convinced that the parking presents such a road safety hazard that an immediate solution is necessary. Preventative measures will undoubtedly result in objections from the school and from parents if no alternative parking is presented and, in response to Danielle’s comments about walking distances, whilst we are entirely aware that current guidance allows for a 2 mile walking route to school for children under 8 and of 3 miles for older children, it is not something we would wish to force on parents without being on firmer ground with regard the hazard that any on-street parking is presenting. | GB/AR and ST to write back and agree the text | same as above | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | MD and Clerk met Matthew Clayton from WBC onsite on 1 Sept and reviewed 15 potential sites.MD and Jay have taken 6 photos of SIDS in situ and sent them to WBC | MD to continue adding remaining sites with WBC | 2 SIDS added Victoria Road and Hammonds Heath | Ongoing | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). | D Kilshaw volunteered |  | Ongoing | G
| 2025-11-28 | Flytipping Drury Lane | Flytipping Drury Lane | Clerk | The Clerk has reported to WBC
| 2025-12-04 | Maintenance of retaining wall in Tower Gardens | Follow up with WBC regarding the maintenance responsibilities for the retaining wall at Tower Gardens and the status of the outstanding planning condition discharges.

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW
| 2022-10-20 | Enforcement reference - ee56e494-c5ac-47bb-8839-a53db19df36c | Closed Fence at 2 Crockers, Mowbray Hill. In breach of condition 3 of the Decision for 22/00319/FULD | Deputy Clerk | Raised new enforcement query on 29/08/25 |  | Closed by Enforcement team on 22/10/25 as they say there is no breach. | To be closed
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in respect (in particular) of the first mobile home on the right-hand side of Birch Lane, entering from West End Road | GB/ST | Chased 29/08/25. response from Adrian Munday 4/9/25 - case was closed on the 28.07.2025. After due investigation, and a tri-party site visit, officers present where unanimously in agreement that three of the legacy park homes had gone and had been replaced with new ones, but on new bases as well; however this does not appear to have resulted in an increase in the overall number of park homes allowed by the site licence which currently stands at 20. The secondary effect of this means that the derelict garage has been removed, and the overgrown area of land and various piles of rubbish had all gone, such that what had remained did not warrant a section 215 Notice in respect of untidy land | There is still a Highways issue with the propery extended into Highways land. Prepare words for email back. | Response sent to Adrian Munday on 14 October with clearer eplanation and photos. WBC to check with Highways Asset Management. Chased 20/11/25 and Adrian Munday forwarded request to John Winstanley. Updte 20/11/25 - WBC have now confirmed that there is an encroachment onto the public highway by the mobile home park that the Highways Maintenance team are aware of and are dealing with. They are currently trying to arrange a collaborative visit between their Highways Contractor and the Police to ensure the works to remove the encroachment go ahead without issue | Ongoing
| 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Deputy Clerk | Chased 29/8.Adrian Munday responded 4/09/25. Site visit is warranted, but he has a high volume of other high priorities | chase before next meeting in December 2025 | Update from WBC on 20/11/25 - low priority - on their list | 2025-12-11
R

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 |  |  | 2025-09-18 | G