## Highways
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-04-02
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Email exchange on 7 July and WBC said they would re-inspect and decide next steps. Chased 22 Aug 2025. A Coxon inspected the route on 11 September 2025. He noted the following: There are a couple of locations where some minor repairs would be useful where surface defects are appearing. Whilst currently it is within the guidelines, there is no doubt the condition will not improve, and maintenance sooner rater than later will be preventative. At this time the whole route is in reasonable condition, however, it will benefit from some improvement in the future. This may be in the form of repairs and surface treatment. If there is any further or new deterioration, especially trip hazards, please log the issue and we will inspect and repair | Review in 9 months time |  | 2026-06-30 | G
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | Update from Edward Crooks on 21 November 2025: 1. My colleague Harriet met with James Strang, the tenant of the field between MOR006 and Dury Lane to discuss the practicalities and what the Estate will do in terms of signage, fencing, gates and the Drury Lane access point. We’re in the process of working up a plan/specification to execute that, getting quotes from contractors etc. 2. I’ve liaised with Steve Davies at T A Fisher over timing from their viewpoint, including the progress of the development, health & safety, Heras fencing etc. I understand that the development is not fully complete yet but they envisage partial opening up of the open space and we’ll keep in touch with them over the timing of the permitted path opening. In summary, it’s moving forward and just a case of finalising what works are required, then agreeing the detail and timing with James and TAF | Monitor | Delayed due to badger set | Ongoing | G
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | Clerk | Andrew Reynolds from WBC responded on 9 October with new process. It was discussed at the Planning meeting on 30 October and Danusia agreed to come up with a response. A response was sent by the office on 4 November as it was agreed that the new process will unlikely improve the current situation. | Follow up | chased WBC on 19 March 2026 | 2025-06-30 | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | Clerk | Edward Crooks sent update on 21 November 2025. West Berkshire had suggested contacting Hampshire to correct an unrecorded section (B–C) of a path caused by errors during the 1991 boundary changes. Hampshire has responded helpfully and outlined two possible options, though one would require a formal delegation of functions between the authorities and would likely be slow and inefficient. Hampshire’s preferred, simpler option is for West Berkshire to record the missing link themselves, either via a Definitive Map Modification Order (to correct an error) or through a Highways Act 1980 creation agreement with the landowner. The next step is to discuss these options with West Berkshire—ideally in person. Meanwhile, the Estate agrees to allow public use of the route marked with purple crosses as a permitted footpath until further notice. | Write to Stuart Higgins | Wrote to Stuart Higgins the Definitive Map Officer at West Berks for an update on 16/12/25. Stuart responed. See letter in meeting papers | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways. Two positive responses - decision left until yellow lines repainted. | On hold. | Email received from resident saying they were happy to pay for half the white lines, but we never went back to them. Jayne prepared response from office. | Ongoing | G
[5 empty] | chased 22/08/2025. Garteh Dowding responded 22/08/25 - The current programme is fully committed for this financial year. However, The Street Mortimer from Strawberryfields to junction with Bloomfield Hatch Lane has been identified for next years programme along with other sites in the District. | Review in 9 months time | Program of works for 2026/2027 wont be signed off until 10 April 2026. WBC say they have a backlog of 250+ and each request will be reviewed in terms of road safetly prioriy. | 2025-06-30 | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | Alex Dryscale from WBC responded 20/11/25. There is no further update on SMPC’s parking requests. Current priorities are three parking scheme consultations (Amendments 35, 36, and the upcoming Amendment 37), so SMPC’s requests are on file for possible inclusion in future schemes. However, more evidence of regular traffic disruption is needed to justify restrictions on the road west of Pitfield Road, as four site visits during school pick-up times showed no routine dangerous or obstructive parking—only occasional issues during special school events. When the area is eventually reviewed, the council will need to work closely with the school to understand their concerns and secure their support, as this helps reduce objections during consultation. Previous proposals have faced significant objections from parents, and despite expectations that children walk to school, many do not, which affects community response to restrictions | Write to WBC to express disappointment that these restrictions were not included in the current public consultation on new parking restrictions, and to seek assurance that they will be included in the next consultation. | Written to Olivia Bailey regarding Parking at station. Olivia Bailey responsded 22 Jan and they confirm they have written to GWR for an update . Chased WBC re yellow lines 10 March 2026 | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | chased 22/08/2025. Responded 27/8/25 - With the reported issue on The Street upwards of Pitfield Lane in particular we would need to investigate whether there is a reasonable and realistic solution to the school parking, as we’re not entirely convinced that the parking presents such a road safety hazard that an immediate solution is necessary. Preventative measures will undoubtedly result in objections from the school and from parents if no alternative parking is presented and, in response to Danielle’s comments about walking distances, whilst we are entirely aware that current guidance allows for a 2 mile walking route to school for children under 8 and of 3 miles for older children, it is not something we would wish to force on parents without being on firmer ground with regard the hazard that any on-street parking is presenting. | Cllr Bridgman agreed to collect photographic evidence to support the case |  | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | 2 SIDS added Victoria Road and Hammonds Heath | MD to continue adding remaining sites with WBC | 6 additional sites were added in January 2026 | Ongoing | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). |  |  | Ongoing | G
| 2025-12-11 | Explore Bus Service to station | Explore up to 30 seater bus to station | Deputy Clerk | Contact TK travel |  | Emailed TK Travel on 16/12/25. TK Travel can provide a 17 seater bus for £55 ph. 350 people responded to Nick's bus survey on extending the No. 2/2A route. The Council’s study found two possible turn-around points, but costs and potential losses led to exploring an on-demand option via the Community Connect scheme. Mortimer is a candidate for this service, awaiting Government funding approval. https://www.westberks.gov.uk/article/41945/West-Berkshire-Community-Connect-On-demand-Transport

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in respect (in particular) of the first mobile home on the right-hand side of Birch Lane, entering from West End Road | GB/ST | Response sent to Adrian Munday on 14 October with clearer eplanation and photos. WBC to check with Highways Asset Management. Chased 20/11/25 and Adrian Munday forwarded request to John Winstanley. Updte 20/11/25 - WBC have now confirmed that there is an encroachment onto the public highway by the mobile home park that the Highways Maintenance team are aware of and are dealing with. They are currently trying to arrange a collaborative visit between their Highways Contractor and the Police to ensure the works to remove the encroachment go ahead without issue | Monitor | No update | 2025-06-30
| 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Deputy Clerk | Update from WBC on 20/11/25 - low priority - on their list | Monitor | Closed 20 March and windows can be changed under permitted development as not listed or in a conservation area | 2026-04-02
| 2025-12-04 | Maintenance of retaining wall in Tower Gardens | Follow up with WBC regarding the maintenance responsibilities for the retaining wall at Tower Gardens and the status of the outstanding planning condition discharges. | Chairman of Committee | Jayne Todd to follow up with WBC and ask who is going to maintain the wall. Ask about kids climbing the wall. |  | Jayne wrote to Paul Henry at WBC on 3 March 2026. Paul Henry wrote back on 12 March suggesting that WBC could potentially take over the maintenance after discussions with TA Fisher and John Winstanley | R
| 19/023/2026 | TRX Frame at Mann's farm | Check with WBC enforcement whether a TRX structure can be up for more than 28 days even if it's only used for 28 days. | Deputy Clerk | Discussed at Planning Meeting on 12 March and Deputy Clerk to write to WBC Enforcement. |  | Deputy Clerk wrote to WBC on 13 March 2026

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 |  |  | 2025-09-18 | G