## Highways
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-04-02
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Email exchange on 7 July and WBC said they would re-inspect and decide next steps. Chased 22 Aug 2025. A Coxon inspected the route on 11 September 2025. He noted the following: There are a couple of locations where some minor repairs would be useful where surface defects are appearing. Whilst currently it is within the guidelines, there is no doubt the condition will not improve, and maintenance sooner rater than later will be preventative. At this time the whole route is in reasonable condition, however, it will benefit from some improvement in the future. This may be in the form of repairs and surface treatment. If there is any further or new deterioration, especially trip hazards, please log the issue and we will inspect and repair | Review in 9 months time |  | 2026-06-25 | G
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | Delayed due to badger set | Monitor |  | Ongoing | G
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | Clerk | chased WBC on 19 March | Follow up |  | 2026-06-25 | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | Clerk | Cllr Bridgman reported that he will address this one once the lease for the cycleway is sorted. | Follow up with Englefield. |  | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways. Two positive responses - decision left until yellow lines repainted. | On hold. | Email received from resident saying they were happy to pay for half the white lines, but we never went back to them. Jayne prepared response from office. | Ongoing | G
[5 empty] | Program of works for 2026/2027 wont be signed off until 10 April 2026. WBC say they have a backlog of 250+ and each request will be reviewed in terms of road safetly prioriy. | Follow up with WBC |  | 2026-06-25 | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | Written to Olivia Bailey regarding Parking at station. Olivia Bailey responsded 22 Jan and they confirm they have written to GWR for an update . Chased WBC re yellow lines 10 March 2026 | Monitor |  | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | Cllr Bridgman agreed to collect photographic evidence to support the case | Cllr Bridgman agreed to collect photographic evidence to support the case |  | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | 6 additional sites were added in January 2026 | MD to continue adding remaining sites with WBC |  | Ongoing | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). |  |  | Ongoing | G
| 2025-12-11 | Explore Bus Service to station | Explore up to 30 seater bus to station | Deputy Clerk | Emailed TK Travel on 16/12/25. TK Travel can provide a 17 seater bus for £55 ph. 350 people responded to Nick's bus survey on extending the No. 2/2A route. The Council’s study found two possible turn-around points, but costs and potential losses led to exploring an on-demand option via the Community Connect scheme. Mortimer is a candidate for this service, awaiting Government funding approval. https://www.westberks.gov.uk/article/41945/West-Berkshire-Community-Connect-On-demand-Transport | Leave with Nick Carter

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in respect (in particular) of the first mobile home on the right-hand side of Birch Lane, entering from West End Road | GB/ST | Response sent to Adrian Munday on 14 October with clearer eplanation and photos. WBC to check with Highways Asset Management. Chased 20/11/25 and Adrian Munday forwarded request to John Winstanley. Updte 20/11/25 - WBC have now confirmed that there is an encroachment onto the public highway by the mobile home park that the Highways Maintenance team are aware of and are dealing with. They are currently trying to arrange a collaborative visit between their Highways Contractor and the Police to ensure the works to remove the encroachment go ahead without issue | Monitor | No update | 2025-06-25
| 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Deputy Clerk | Closed 20 March and windows can be changed under permitted development as not listed or in a conservation area | Write to planning enforcement to say we don't agree its permitted development. |  | 2026-06-25
| 2025-12-04 | Maintenance of retaining wall in Tower Gardens | Follow up with WBC regarding the maintenance responsibilities for the retaining wall at Tower Gardens and the status of the outstanding planning condition discharges. | Chairman of Committee | Jayne wrote to Paul Henry at WBC on 3 March 2026. Paul Henry wrote back on 12 March suggesting that WBC could potentially take over the maintenance after discussions with TA Fisher and John Winstanley | Cllr Bridgman to respond to Paul Henry to say we and TA Fisher are happy for WBC to take over the maintenance of public open space and retaining wall. |  | R
| 19/023/2026 | TRX Frame at Mann's farm | Check with WBC enforcement whether a TRX structure can be up for more than 28 days even if it's only used for 28 days. | Deputy Clerk | A planning application has been raised by Manns Farm | monitor |  | 2026-06-25

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 |  |  | 2025-09-18 | G