## Highways
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2025-09-18
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | DEADLINE | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Emails sent to WBC (A Coxon) on 10/10/24, 05/12/24, 17/12/24 and 09/01/25. Chased again 24/06/25 - response 26/06/25 (no funding this year and will reinspect). | Need to wait for WBC to have funding in 26/27? Follow up re previous promises. | Email exchange on 7 July and WBC said they would re-inspect and decide next steps. Chased 22 Aug 2025. A Coxon responded same day and will attempt to update us by 18 September 2025 | Ongoing | A
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | See letter 13/03/2020 from Englefield Estate (and enclosed copy letter of same date to WBC) confirming intention to provide new permissive path. | Awaiting establishment of public open space and paths around SUDS ponds. | No change. | Ongoing | G
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | DM/Clerk | Email to WBC 29/11/24 and reference at District/Parish Conference 30/04/25. WBC (K Adu-Gyamfi) chased 24/06/25. | Continue to chase. | chased Kofi Adu-Gyami on 22/08/2025. Response received 25/8/25. Kofi has chased with relevant team and they should be contacting interested parishes soon. | Ongoing | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | GB/Clerk | Email to Englefield Estate (landowners) 19/11/24. Response for Estate (E Crookes) - will review. Chased 28/03/25, response from Estate 31/03/25 re contacting WBC etc. Chased again 24/06/25. | Continue to chase. | chased 22/08/2025. Edward Crookes responded 26/8 and said he had visited the path about 10 days ago and has contacted Stuart Higgins the Definitive Map officer at WBC and is waiting to hear back to put the necessary conditions in hand. | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways. Two positive responses - decision left until yellow lines repainted. | On hold. |  | Ongoing | G
[5 empty] | Existing yellow lines part done, but poorly. Email to WBC (G Dowding) 15/01/25 - response promising to take up with maintenance team. | Chase. | chased 22/08/2025. Garteh Dowding responded 22/08/25 - The current programme is fully committed for this financial year. However, The Street Mortimer from Strawberryfields to junction with Bloomfield Hatch Lane has been identified for next years programme along with other sites in the District. | Ongoing | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | Emails with WBC (A Drysdale) - can add this to scheme being drafted. Email to WBC 29/05/25 asking to be added (18 mth consultation?). Email to WBC 24/06/25 for update. | Chase as necessary. | chased 22/08/2025. Alex Drysdale responded 27/08/25 and said current position is that the request will remain on file and not be included in any immediate parking scheme | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | Emails with WBC (A Drysdale) referencing strong opposition previously from school (and parents?). Email to WBC 24/06/25 for update. | Chase as necessary. | chased 22/08/2025. Responded 27/8/25 - With the reported issue on The Street upwards of Pitfield Lane in particular we would need to investigate whether there is a reasonable and realistic solution to the school parking, as we’re not entirely convinced that the parking presents such a road safety hazard that an immediate solution is necessary. Preventative measures will undoubtedly result in objections from the school and from parents if no alternative parking is presented and, in response to Danielle’s comments about walking distances, whilst we are entirely aware that current guidance allows for a 2 mile walking route to school for children under 8 and of 3 miles for older children, it is not something we would wish to force on parents without being on firmer ground with regard the hazard that any on-street parking is presenting. | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | New. | MD and Clerk to decide on which street furniture to seek permission to use for new SIDs. | MD and Clerk met Matthew Clayton from WBC onsite on 1 Sept and reviewed potential sites. MD and Clerk need to take photos of the SIDs in situ. | 2025-09-18 | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). | Follow up. |  | Ongoing | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Draft response prepared. | MD and Clerk to prepare final letter and add speeding data for 2025. | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 | 2025-09-18 | G

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | DEADLINE
| 2022-10-20 | Enforcement reference - ee56e494-c5ac-47bb-8839-a53db19df36c | Closed Fence at 2 Crockers, Mowbray Hill. In breach of condition 3 of the Decision for 22/00319/FULD | Assistant Clerk | Raised new enforcement query on 29/08/25 |  |  | Ongoing
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in respect of Birch Lane | Assistant Clerk | No update. Nick Carter spoke to Enforcement team in July |  | Chased 29/08/25. response from Adrian Munday 4/9/25 - case was closed on the 28.07.2025. After due investigation, and a tri-party site visit, officers present where unanimously in agreement that three of the legacy park homes had gone and had been replaced with new ones, but on new bases as well; however this does not appear to have resulted in an increase in the overall number of park homes allowed by the site licence which currently stands at 20. The secondary effect of this means that the derelict garage has been removed, and the overgrown area of land and various piles of rubbish had all gone, such that what had remained did not warrant a section 215 Notice in respect of untidy land | Ongoing
| 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Assistant Clerk | Raised 30 June 2025 |  | Chased 29/8.Adrian Munday responded 4/09/25. Site visit is warranted, but he has a high volume of other high priorities

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed