## Highways (hidden)
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-04-02
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Email exchange on 7 July and WBC said they would re-inspect and decide next steps. Chased 22 Aug 2025. A Coxon inspected the route on 11 September 2025. He noted the following: There are a couple of locations where some minor repairs would be useful where surface defects are appearing. Whilst currently it is within the guidelines, there is no doubt the condition will not improve, and maintenance sooner rater than later will be preventative. At this time the whole route is in reasonable condition, however, it will benefit from some improvement in the future. This may be in the form of repairs and surface treatment. If there is any further or new deterioration, especially trip hazards, please log the issue and we will inspect and repair | Review in 9 months time | Alan Coxon from WBC responded on 02/06/26 to say no planned project and low priority but the path is being monitored. Are we aware of any grant funding. | 2027-04-01 | G
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | Graham wrote to Edward Crooks at Englefield on 28 May 2026 for an update. Edward Crooks at Englefield responded 5 June 2026. Due to a badger set another route is being explored. | Monitor | New blue route to avoid badger set will be fenced on 17 August 2026 | Ongoing | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | Clerk | Cllr Bridgman reported that he will address this one once the lease for the cycleway is sorted. | Follow up with Englefield. | Graham wrote to Edward Crooks at Englefield on 28 May 2026 for an update and sent a s30 draft agreement. Edward Crookes responded 5th June with some options.Graham responded 8 June. Hants failed to record a footpath. Graham suggests SMPC and Englefield to agree an S30 and WBC to record a new PROW to link across the gap.WBC and Hants are in discussions. | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Action to write to residents regarding white lines across driveways. Two positive responses - decision left until yellow lines repainted. | On hold. | Email received from resident saying they were happy to pay for half the white lines, but we never went back to them. Jayne prepared response from office. | Ongoing | G
[5 empty] | Program of works for 2026/2027 wont be signed off until 10 April 2026. WBC say they have a backlog of 250+ and each request will be reviewed in terms of road safetly prioriy. | Follow up with WBC | chased Alex Drysdale 26/05/26. He responded 27 May that nothing is set in stone for the new works program for 26-27. All based on priority. To call a site meeting to discuss the various parking issues on the Street. Julie taking over his role. | Ongoing | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | Written to Olivia Bailey regarding Parking at station. Olivia Bailey responsded 22 Jan and they confirm they have written to GWR for an update . Chased WBC re yellow lines 10 March 2026 | Monitor | Olivia Bailey is setting up a meeting with GWR and we will be invited. | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | Cllr Bridgman agreed to collect photographic evidence to support the case | Cllr Bridgman agreed to collect photographic evidence to support the case | Cllr Bridgman will collect photos | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | 6 additional sites were added in January 2026 | MD to continue adding remaining sites with WBC |  | Ongoing | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). |  |  | Ongoing | G

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in Birch Lane, entering from West End Road | GB/ST | WBC say an arrangement was reached with the owner/occupier and works to reinstate the highway boundary have been undertaken. Cllr Bridgman has written to Highways to suggest to them that it is not correct that the highways boundary follows the line of mature trees along the lane and that the fence is the boundary and not the tree line. | monitoring | No new updates | 2026-08-27
| 2025-12-04 | Maintenance of retaining wall in Tower Gardens | Follow up with WBC regarding the maintenance responsibilities for the retaining wall at Tower House Farm and the status of the outstanding planning condition discharges. | Chairman of Committee | JT suggested we write to WBC to ensure adherence to original planting in relation to maintenance of the open space | JT still needs to write to WBC | No update | 2026-08-27

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 |  |  | 2025-09-18 | G
| 2025-12-11 | Explore Bus Service to station | Explore up to 30 seater bus to station | Deputy Clerk | Emailed TK Travel on 16/12/25. TK Travel can provide a 17 seater bus for £55 ph. 350 people responded to Nick's bus survey on extending the No. 2/2A route. The Council’s study found two possible turn-around points, but costs and potential losses led to exploring an on-demand option via the Community Connect scheme. Mortimer is a candidate for this service, awaiting Government funding approval. https://www.westberks.gov.uk/article/41945/West-Berkshire-Community-Connect-On-demand-Transport | Leave with Nick Carter
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | Clerk | chased WBC on 19 March | Follow up | chased with Andrew Reynolds at WBC on 26/05/2026. Response from WBC on 18 June doesn't change the process for urgent removal of overhanging vegetation | 2026-06-25 | G
|  | 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Deputy Clerk | Closed 20 March and windows can be changed under permitted development as not listed or in a conservation area | Write to planning enforcement to say we don't agree its permitted development. | Enforcement have written to say they still believe it falls under permitted development. Even though the glazed bars have been removed the replacement windows are considered to retain a similar appearance | 2026-07-16