## RFC Action Tracker
Estate Management Committee Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-10-08
Ref | Original Date | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE MEETING | DEADLINE | RAG*
25/009 5 | 2025-05-22 | Fairground information boards | R Saunders to develop draft designs and explore potential suppliers | RS |  | SH will forward the previous info about the boards to the Office and RS. |  | 2025-08-01 | R
| 2026-04-16 | Tree planting | Amelanchier to be planted in Autumn. | Clerk |  |  | The Clerk will arrange for purchase and install in November due to lack of rain | 2026-10-01 | G
26/006 | 2026-07-09 | WE Road Carpark border | The Clerk is to organise quotes for weeding of the WE road carpark and use the available budget line to get the work done. | Clerk | Added at last meeting- see action |  | Committee Chairman asked the Clerk to see if Greening Mortimer would be willing to help again instead of organising a gardening. No response received from Greening Mortimer. The Clerk will proceed with a gardener to tidy up the border. | 2026-10-08
26/008.6 | 2026-07-09 | Community Defib at St Mary's school | The Clerk to apply for defib via British Heart Foundation and correspond with school. | Clerk | Added at last meeting- see action |  | The Clerk has applied for this with BHF | 2026-10-08
26/008.8 | 2026-07-09 | Windmill Road/FG footpath | The Clerk/Cllr Kilshaw to get quotes for 20 tonnes of golden gravel, a mini digger, and a dumper truck | Clerk | Added at last meeting- see action |  | This will be quoted for following he completion of the Mortimer to Burghfield Cycleway due to capacity | 2026-10-08

## Previous
Ref | Original Date | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE MEETING | DEADLINE | RAG*
25/009-4.a | 2025-05-22 | Cemetery extension ongoing maintenance | The Clerk to contact current maintenanc eprovider (Tactical) to get a spec and a quote for ongoing mainteneance contract. | Clerk |  |  | Meeting with tactical booked 12/6/2025, awaiting quote | 2025-07-24 | G
22-018 2 | 2022-10-20 | War Memorial Remedial Works | Repair the mortar with lime mortar | Clerk/SH/ Custodian | The War Memorial was cleaned in October 2023. Confirmed with SH that from May 2025 - the mortar works need undertaking and brass needs cleaning. SH offered a date of 20 June but no Cllrs could attend. | SH will contact Mr N Mortimer for a further date. |  | 2025-08-31 | R
25/015 3 | 2025-05-22 | Fairground Fence | R Saunders and S Hill to create a spec for the replacement of the Fairground Fence running along The Street. | RS/SH | Spec sent out with return of 1.10.2025 | Asked Saunders and AES to requote for correct measurements 09/10/2025 |  | 2025-08-01 | R
25/037 | 2025-10-09 | Key box | To install a keybox at the Horse and Groom with temergency access to the Fairground keys | SH/Clerk | Key box has been ordered | The key box has arrived ands the clerk will ask the parish custodian to install. |  | 2026-01-22 | A
25/012 | 2025-05-22 | Electricity cabinets remedial work | Following a request to alter quotes in February 2025 Stanley Electrical services still need to alter remedial works quotes | Clerk | A Meeting was held on 16/01/2026 with Stanley Electrical Services/ The Clerk/ D Kilshaw to review the original quotes. | The Clerk explained |  | 2025-07-10 | R
25/054 | 2026-01-22 | Utility square uses | The Clerk to investigate the cost and options for a collapsible or telescopic flag and to confirm the hole diameter (approx. 12 inches) | Clerk/KS |  |  |  | 2026-04-16 | G
25/039-1 | 2025-10-09 | Cemetery regulations and fees | To recivew the cemetery regulations and fees to reflect the memorial wall plaques. | GB/Clerk | This will be prepared for the meeting on 9 July 2026. |  | Cllr Bridgman has proposal for meeting on 9 July 2026 for resolution, the Clerk has investigated an option for costings for review at meetig on 9 July 2026 | 2026-01-22 | A
25/057 | 2026-01-22 | Cemetery extension mapping | Cllr Kilshaw to prepare a cemetery map for the Office to assist with the recording of the cemetery plots in the extension. | DK |  |  |  | 2026-04-16 | G
26/008.9 | 2026-07-09 | WE Road WBC W charger proposal | The Clerk to respond to Cllr Carter with Committee decision. | Clerk | Added at last meeting- see action |  |  | 2026-10-08
26/008.7 | 2026-07-09 | Grazing area | The Clerk to get back in touch with the resident who requested signage, advise it will be publicised on FB/newsbulletins and noticeboards. | Clerk | Added at last meeting- see action |  |  | 2026-10-08
26/008.5 | 2026-07-09 | RoSPA | The Clerk to gather quotes for: - Repair of large horse - Replace worn chains on Swing dome -Replace worn chains on Titan -Squeaking chains on the 2 bay swing in the under 8s inspected | Clerk | Added at last meeting- see action |  |  | 2026-10-08
26/008.4 | 2026-07-09 | Tree Surveys | The Clerk to gather quotes as per the Tree survey for moderate and low priority works | Clerk | Added at last meeting- see action |  |  | 2026-10-08
26/008.7 | 2026-07-09 | Grazing area | The Clerk to get back in touch with the resident who requested signage, advise it will be publicised on FB/newsbulletins and noticeboards. | Clerk | Added at last meeting- see action |  |  | 2026-10-08