## Highways (hidden)
Highways Action Tracker
*RAG – Green, will be completed on time; Amber, delayed but should eventually be completed on time; Red, not going to be completed on time
Meeting: | 2026-04-02
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW | RAG*
22/18.4 | 2022-10-20 | Victoria Rd/Croft Rd/West End Rd Footpath (STRA/33) | WBC arranging for the footpath to be resurfaced with Flexipave. Check if and when the resurfacing works are being undertaken. | Clerk | Alan Coxon from WBC responded on 02/06/26 to say no planned project and low priority but the path is being monitored. Asked if we are aware of any grant funding. | Monitoring. |  | Ongoing | G
24/021.6 | 2024-10-17 | Footpath leading from West End Road near the APMF to Drury Lane (STRA/42/43) | Seek to connect footpaths as one PROW (part currently goes into Hants but is unaccessible). | Clerk | Graham wrote to Edward Crooks at Englefield on 28 May 2026 for an update and sent a s30 draft agreement. Edward Crookes responded 5th June with some options.Graham responded 8 June. Hants failed to record a footpath. Graham suggests SMPC and Englefield to agree an S30 and WBC to record a new PROW to link across the gap.WBC and Hants are in discussions. | Email was received on 17 September from Edward Crooks and there had not been | chased Edward Crooks for update on 25 August 2026 | Ongoing | G
24/021.7 | 2024-10-17 | St Marys School and The Steet parking, parking restrictions, etc | Repainting of yellow and white lines | GB/Clerk | Email received from resident saying they were happy to pay for half the white lines, but we never went back to them. Jayne prepared response from office. | On hold. |  | Ongoing | G
[5 empty] | chased Alex Drysdale 26/05/26. He responded 27 May that nothing is set in stone for the new works program for 26-27. All based on priority. To call a site meeting to discuss the various parking issues on the Street. Julie taking over his role. | Waiting for WBC | A teams meeting was held by West Berks on 30 July 2026. | Ongoing | G
|  |  | Additional parking restrictions from Chuch Lane to Church Farm Barns | GB/Clerk | Olivia Bailey is setting up a meeting with GWR and we will be invited. | Monitor | chased for update 25 August 2026 | Ongoing | G
|  |  | Additional parking restrictions from Pitfield Lane up The Street | GB/Clerk | Cllr Bridgman will collect photos |  |  | Ongoing | G
25/027.2 | 2025-06-26 | SIDS & ASWC | Review sites for new SIDs | MD/Clerk | MD to continue adding remaining sites with WBC |  |  | Ongoing | G
|  |  | Advertise for additional ASWC volunteers | Clerk | Ongoing (from previous meetings). |  |  | Ongoing | G

## Planning
REF | ORIGINAL DATE | SUBJECT | ACTION | BY | STATE AS AT LAST MEETING/ENTRY | DECISION AT MEETING | UPDATE SINCE LAST MEETING/ENTRY | REVIEW
| 2023-11-23 | Enforcement enquiry 23/00274/16OTHR | Planning enforcement action in Birch Lane, entering from West End Road | GB/ST | WBC say an arrangement was reached with the owner/occupier and works to reinstate the highway boundary have been undertaken. Cllr Bridgman has written to Highways to suggest to them that it is not correct that the highways boundary follows the line of mature trees along the lane and that the fence is the boundary and not the tree line. | monitoring | No new updates | 2026-12-10
| 2025-12-04 | Maintenance of retaining wall in Tower Gardens | Follow up with WBC regarding the maintenance responsibilities for the retaining wall at Tower House Farm and the status of the outstanding planning condition discharges. | Chairman of Committee | JT suggested we write to WBC to ensure adherence to original planting in relation to maintenance of the open space. WBC has responded and will take over the site in Winter 2026 | monitoring | Deputy Clerk forwarded correspondance from WBC to the Committee | 2026-12-10
| 2026-09-17 | Path to the right of Windmill Court is narrower than shown on plans | Clerk has written to Sovereign | Clerk | Clerk had meeting with Sovereign who said they don’t think they can fit a path in. Sovereign to investigate further. | GB and Clerk to follow up with Soverign and confirm there will be a path between Windill Court and 29 Windmill Road | Soverign said path will be as per the plans. | 2026-12-10

## Previous
ITEM | DATE of Meeting/ Report | SUBJECT | ACTION | BY WHOM | CURRENT STATE AS AT MEETING DATE /LAST ENTRY | DECISION AT MEETING (IF ANY) | UPDATE SINCE MEETING | DEADLINE | RAG*
|  |  | Add to full Council agenda re councillors as volunteers | Clerk | Ongoing |  |  | Ongoing
25/012 | 2025-06-05 | Soul Barns Planning complaint | Pass MOP complaints onto planning enforcement at WBC | Clerk | Raised with the WBC Enforcement Team 23/06/25 | Remove from Trakcer | Task completed | 2025-06-26
|  | Source Litium batteries for new SIDs | DK | DK | Clerk checking with DK. |  | Task completed
24/008.4 | 2024-06-20 | PROWs | Secure report of current PROW issues Add link and information on PROWs on SMPC website | GB/Clerk | GB working on making the WBC spreadsheet more readable and identifying the sites - still in progress. | Deadline extended. | GB sent out PROW spreadsheet on 14 July 2025 | 2025-09-18 | G
25/010.1 | 2025-06-05 | Olivia Bailey Letter | Response to correspondence Olivia Bailey MP sent to residents of The Street (and adjacent) re speeding. | Clerk/MD | Response sent to Olivia Bailey 15 July 2025. chased 22/08/25 |  |  | 2025-09-18 | G
| 2025-12-11 | Explore Bus Service to station | Explore up to 30 seater bus to station | Deputy Clerk | Emailed TK Travel on 16/12/25. TK Travel can provide a 17 seater bus for £55 ph. 350 people responded to Nick's bus survey on extending the No. 2/2A route. The Council’s study found two possible turn-around points, but costs and potential losses led to exploring an on-demand option via the Community Connect scheme. Mortimer is a candidate for this service, awaiting Government funding approval. https://www.westberks.gov.uk/article/41945/West-Berkshire-Community-Connect-On-demand-Transport | Leave with Nick Carter
24/012.5 | 2024-10-17 | Hedges | Liaise with WBC re overgrown hedges and establish what SMPC can do to assist/enforce. | Clerk | chased WBC on 19 March | Follow up | chased with Andrew Reynolds at WBC on 26/05/2026. Response from WBC on 18 June doesn't change the process for urgent removal of overhanging vegetation | 2026-06-25 | G
|  | 2025-06-30 | Enforcement Enquiry 25/00259/05NOAC | Lime Tree Cottage Windows not in keeping | Deputy Clerk | Closed 20 March and windows can be changed under permitted development as not listed or in a conservation area | Write to planning enforcement to say we don't agree its permitted development. | Enforcement have written to say they still believe it falls under permitted development. Even though the glazed bars have been removed the replacement windows are considered to retain a similar appearance | 2026-07-16
23/087.2 | 2023-11-23 | MOR006 Footpath | Monitor the build of the new footpath to the far south-west corner that will link to the informal footpath running through Englefield Estate's land and connecting to Drury Lane. | Clerk | New blue route to avoid badger set will be fenced on 17 August 2026 | Monitor | Route completed 17 August 2026 | Done | G